ACQUISITION STRATEGY

[or]

TECHNOLOGY DEVELOPMENT STRATEGY

(If Pre–Milestone A)

FOR

[PROGRAM NAME]

[Sample Outline]

20 April 2011

Version 1.0, 04/20/2011

PROGRAM NAME

SUBMITTED BY:

_____________________________     _______

Date

wwwwwwwwwwwwwwwwwww

Program Manager, program name

CONCURRENCE:

_____________________________     _______

Date

xxxxxxxxxxxxxxxxxxxx

Program Executive Officer (PEO)

_____________________________     _______

Date

yyyyyyyyyyyyyyyyyyyyyy

DoD Component Acquisition Executive (CAE)

APPROVAL:

_____________________________     _______

Date

zzzzzzzzzzzzzzzzzzzzzzz

Under Secretary of Defense (Acquisition, Technology and Logistics)   (or as applicable)

[Note: Include a Table of Contents]

Purpose.  State the reason the program strategy (i.e., the Technology Development Strategy or the Acquisition Strategy) is being prepared or updated (e.g., milestone review, full rate production decision, change in strategy, etc.).

Capability Need

Summarize the requirement. Indicate the key operational and sustainment requirements for this system (i.e., the time-phased capability requirements as described in the Initial Capabilities Document, Capability Development Document, and/or Capability Production Document). Highlight system characteristics driven by interoperability and/or joint integrated architectures, capability areas, and family- or system-of-systems.

Explain the choice of product or service description types (including performance-based acquisition descriptions) to be used in the acquisition (FAR 7.105(b)(7)).

State all significant conditions affecting the acquisition, such as (i) Requirements for compatibility with existing or future systems or programs and (ii) Any known cost, schedule, and capability or performance constraints (FAR 7.105(a)(2)).

Summarize the expected operational mission of this program. Identify the user and summarize the user‘s Concept of Operations (CONOPS). Indicate how the program fits into current and future integrated architectures.

Summarize the threat assessment in relation to the capabilities or operational concepts the system will support (see the applicable System Threat Assessment document for details).  Specify which elements of the threat (if any) are not yet fully defined, and which elements of the threat (if any) will not currently be countered by the system capabilities or CONOPS.  Include a projected plan/schedule to define and counter the remaining threat elements.

If this is a Technology Development Strategy, summarize the Net-Centric Data Strategy, as required by DoD Directive 8320.02.  At subsequent milestone decisions, summarize the Net-Centric Data Strategy in the Information Support Plan.

Include an Operational View (OV)-1 Illustration.  (See example in Figure 1, below.)

Figure 1.  Example OV-1 Illustration

For Milestone B, provide a reference design concept for the product showing major subsystems and features (one or more drawings as needed to describe or illustrate the expected features of the product; see the example in Figure 2).

- Figure 2.  Sample Drawing of the Reference Design Concept

Acquisition Approach.  Indicate whether the program strategy will be evolutionary or single step to full capability.  Note: If this program employs an evolutionary acquisition approach, this strategy will primarily apply to the current increment, while occasionally addressing some topics in the context of the overall program.

If this program employs an evolutionary acquisition approach, summarize the cost, schedule, and performance drivers for the increment under consideration, and the plan to transition from the initial increment to later increments.

Specify any unique program circumstances, such as transitioning from a technology project, selection as a special interest program, etc.

Indicate whether this program will replace an existing system, is a modification to an existing system, or is a new capability.

Indicate whether this is a New Start program. Verify that the appropriate Congressional notifications have been completed for a New Start. (Reference DoD 7000.14-R, DOD Financial Management Regulation, Volume 3, Chapter 6 for guidance on new start determinations.)

Indicate whether this is a joint program. If so, specify the joint nature and characteristics of the program. Identify the Service(s) or DoD Components involved, state the key Service-specific technical and operational differences in the end item deliverables, and provide the principal roles and responsibilities of each DoD Component in the management, execution, and funding of the program.

If this is a Technology Development Strategy, identify the feasible technical approaches for developing the approved materiel solution, the impact of prior acquisitions on those approaches, and any related preceding effort.

If this strategy supports the Milestone B or C decision, in a table showing quantity per year, indicate the total planned production quantity and provide the LRIP quantity.  Summarize the Low-Rate Initial Production (LRIP) plan.  If the planned LRIP quantity exceeds ten percent of the total planned production quantity, provide the justification.  (Not applicable to software-intensive programs without production components.)

Tailoring

Consistent with statutory and federal regulatory requirements, the Program Manager (PM) and Milestone Decision Authority (MDA) may tailor the phases and decision points to meet the specific needs of the program.  If tailoring is planned, state what is being proposed and why.

List all requests for either regulatory policy waivers or waivers permitted by statute.  Include a table similar to notional Table 1.

| WAIVER REQUESTS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Requirement to Be Waived | Type: Regulatory or Statutory | Granting Authority | Rationale | Required by [date or event] | Status |

Table 1.  Notional Table of Program Waiver Requests

If specifically designated by the requiring agency as a program subject to acquisition streamlining, discuss plans and procedures to:  (i) Encourage industry participation by using draft solicitations, presolicitation conferences, and other means of stimulating industry involvement during design and development in recommending the most appropriate application and tailoring of contract requirements; (ii) Select and tailor only the necessary and cost-effective requirements; and (iii) State the timeframe for identifying which of those specifications and standards, originally provided for guidance only, shall become mandatory (FAR 7.105(a)(8)).

Program Schedule

Provide a detailed graphic illustrating program milestones, phases, and events.  Depicted events will vary by program, but will minimally include key acquisition decision points; principal systems engineering and logistics activities such as technical reviews and assessments; planned contracting actions such as request for proposal (RFP) release, source selection activity, and contract awards; production events and deliveries; and key test activities. (Figure 3 is a notional depiction of the expected level of detail.  For example, contract details will vary with the contracting approach and the plan for competition and multiple suppliers; the use of options, re-competes, and/or new negotiated sole source; etc.)

Milestones for the acquisition cycle. Specifically, address the following steps, as well as any others that may be appropriate (FAR 7.105(b)(21)):

- Acquisition plan approval.

- Statement of work.

- Specifications.

- Data requirements.

- Completion of acquisition-package preparation.

- Purchase request.

- Justification and approval for other than full and open competition where applicable and/or any required D and F approval.

- Issuance of synopsis.

- Issuance of solicitation.

- Evaluation of proposals, audits, and field reports.

- Beginning and completion of negotiations.

- Contract preparation, review, and clearance.

- Contract award.

Indicate the basis for establishing delivery or performance-period requirements.  Explain and justify any urgency if it results in concurrency of development and production or constitutes justification for not providing for full and open competition.

Summarize the analysis justifying the proposed program schedule (list analogous programs or models used to derive schedule).

Briefly discuss the activities planned for the phase following the milestone (or other decision event) for which approval is sought.

Ensure test strategy milestones (DT&E, OT&E, etc.) are included in your schedule.

Figure 3.  Notional depiction of the Integrated Schedule for Program

Interdependencies.  Specify programmatic interdependencies with other programs.  Discuss the relationship of the interdependencies with program activity on the critical path.  If any memorandums of agreement are required to formalize these relationships/interfaces, list them in the format presented in Table 2. Identify the interface (i.e., the system this product interfaces with); the agency that owns the other system; the authority (e.g., PEO, CAE, delegated PM) responsible for controlling the interface (i.e., the individual who can set the requirement; direct the solution to the interface issue; and direct who provides the funding for the solution); the required by date; and the impact if not completed.

| REQUIRED MEMORANDA OF AGREEMENT |  |  |  |  |
| --- | --- | --- | --- | --- |
| Interface | Cooperating Agency | Interface Control Authority | Required By Date | Impact if Not Completed |

Table 2.  Notional table of Required Memoranda of Agreement

If using an evolutionary acquisition approach with concurrent increments, state the relationship between the milestones and activities in one increment to those in the other increment(s).  Include criteria for moving forward to subsequent phases of the same or other increments.

Risk and Risk Management

Summarize the approach used to identify, analyze, mitigate, track, and control performance/technical/manufacturing cost, schedule, sustainment, and programmatic risk throughout the life of the program.

List and assess any program interdependency issues that could impact execution of the acquisition strategy.  If the program is dependent on the outcome of other acquisition programs or must provide capabilities to other programs, the nature and degree of risk associated with those relationships should be specified.  Summarize how these relationships and associated risk will be managed at the PM, PEO, and DoD Component levels.

List the key program technologies, their current technology readiness levels (TRL), the basis for including a technology (e.g., available alternative or low-risk maturation path) if it is below the TRL 6 benchmark for Milestone B, and the key engineering and integration risks.  NOTE: Key technologies should include those technologies that are part of the system design and those associated with manufacturing the system.

If conducted, summarize the results of the Technology Readiness Assessment.

Summarize technology maturation plans and risks for each key technology, engineering risk, and integration risk identified.

Briefly explain how the program‘s strategy is appropriate given the maturity of the system technology and design.

If the strategy is for the Technology Development Phase:

Identify alternate technologies that could be employed if a technology chosen for the system does not achieve the maturity necessary to incorporate it into the baseline system design and define their impact on system performance and cost.

Identify the specific prototyping activities that will be conducted during Technology Development and specify how those activities and any others planned for Engineering and Manufacturing Development will be used to reduce program cost, schedule, and/or performance risk.

Identify the principal programmatic risks (e.g., staffing, resources, infrastructure, industrial base, etc.) and summarize mitigation plans, including key risk-reduction events.

Identify any risks that have been deferred to future increments. Explain why these risks were deferred and whether any residual risks remain in this increment.

The acquisition strategy at the Full-Rate Production/Full Deployment Decision Review should identify principal manufacturing (if applicable)/sustainment/operational risks, and summarize mitigation plans, to include key risk reduction events.

Identify any risk with the test strategy.  Test strategy risk should include potential lack of availability of testing assets such as aircraft, labs, resources, etc.

For Information Assurance, ensure the IA Risk Management framework is utilized.

Business Strategy

Competition Strategy.  Explain how a competitive environment will be sought, promoted, and sustained throughout all program phases.

Summarize the competition strategy for the upcoming phase

In situations where head-to-head competition is not possible, explain how dissimilar competition or other competitive approaches will be used

Indicate how the results of the previous acquisition phase impact the competition strategy for the approaching phase

Indicate how the competition strategy facilitates execution of the acquisition strategy

Market Research. Summarize the research conducted and the results of market research. Indicate the specific impact of those results on the various elements of the program.  Summarize plans for continuing market research to support the program throughout development and production.  Market research information provided in the strategy should be sufficient to satisfy the requirements of 10 United States Code (USC) 2366a and 10 USC 2366b.  For more information, see Federal Acquisition Regulation (FAR) Part 10, Market Research, and Defense Federal Acquisition Regulation Supplement (DFARS) section 210.001).

Advance Procurement. Indicate whether advance procurement of long lead items is planned.  List highest dollar value items.  The Technology Development Strategy/Acquisition Strategy must clearly indicate the intention to employ advance procurement.  NOTE: The MDA must separately and specifically approve advance procurement if authorization is sought prior to the applicable milestone decision. See Defense Acquistion Guidebook (DAG) Chapter 2 for additional information.

Sustainment Strategy.  The details of program sustainment planning are included in the Life Cycle Sustainment Plan, which will be prepared and approved as a separate document.  This portion of the strategy should:

Specify the contracting strategy to provide product support throughout the system life cycle. The sustainment strategy should reflect the Maintenance or Support CONOPS and consider: impacts to system capability requirements; responsiveness of the integrated supply chains across government and industry; maintaining long-term competitive pressures on government and industry providers; and providing effective integration of weapon system support that is transparent to the warfighter and provides total combat logistics capability.

State the assumptions used in determining whether contractor or agency support will be employed, both initially and over the life of the acquisition, including consideration of contractor or agency maintenance and servicing (see FAR Subpart 7.3), support for contracts to be performed in a designated operational area or supporting a diplomatic or consular mission (see FAR section 25.301); and distribution of commercial items.*

* Note: Items marked with an asterisk (*) in this section are not required for the Technology Development Phase or Technology Development Strategy.

Provide an overview of the sustainment-related contract(s) including how the integrated product support package will be acquired.  The discussion should provide:

The performance measures being used (including the extent to which it is traditional transaction based/process focused and performance-based/outcome focused);

The portion of the system covered with the associated sustainment-related functions;

How the support concept ensures integration with other logistics support and combat support functions to optimize total system availability while minimizing cost and the logistics footprint;

How the product support strategy will ensure the selection of best value support providers, maximize partnering, and advocate integrated logistics chains in accordance with DoD product support objectives;

How manpower and spares will be optimized;*

Efforts to ensure secure and integrated information systems across industry and government that enable comprehensive supply chain integration and full asset visibility;*

Dedicated investments needed to achieve continuous improvement of weapon system supportability and reduction in operating costs;

How performance expectations (as defined in performance agreements) will be compared to actual performance results (post Milestone C);*

If Interim Contract Support (ICS) is planned, the ICS requirements, approach, and a plan to transition to normal sustainment support.*

If the strategy includes contractor logistics support (CLS), indicate how CLS contract flexibility will support the sustainment concept;* and

How the program will ensure product support integration throughout the system life cycle.

Ensure the test strategy aligns with and supports the sustainment strategy.

Contract(s) Planned.  For each contract including all options (FAR 7.105(b)(3)):

Provide a table (see example Table 3) that identifies the purpose, type, value, performance period, and deliverables of the contract.

| MAJOR CONTRACTS |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Contract | Purpose | Type | Value | Performance Period | Major Deliverables |

Table 3. Notional Table of Major Contracts

Specify what the basic contract buys; how major deliverable items are defined; options, if any, and prerequisites for exercising them; and the events established in the contract to support appropriate exit criteria for the phase or intermediate development activity.

Identify the contract type(s) and period(s) of performance.  The acquisition strategy shall provide the information necessary to support the decision on contract type. (See FAR Part 16 and Section 818, Public Law (P.L.) 109-364 for additional direction.)

Address the alignment of the contract with the overarching acquisition strategy and the competition strategy.

Indicate whether a competitive award, sole source award, or multiple source development with down select to one production contract is planned.

If expecting to use other than full and open competition, cite the authority and indicate the basis for applying that authority, identify source(s), and explain why full and open competition cannot be obtained.

Indicate how subcontract competition will be sought, promoted, and sustained throughout the course of the acquisition. Identify any known barriers to increasing subcontract competition and address how to overcome them.

Specify breakout plans for each major component or sub-system as well as spares and repair parts.

Assess the comparative benefits of awarding a new contract vice placing a requirement under an existing contract. (10 USC 2306, 10 USC 2304.)

If planning to award a new indefinite delivery contract, indicate how many contracts are planned to be awarded.  If a single award is planned, explain why multiple awards are not feasible.  Indicate the ordering period.

Undefinitized contracts.  Indicate if an undefinitized contract will be awarded and provide the rationale.  Identify steps to avoid using an undefinitized contract, and list the planned incentives to motivate the contractor to achieve timely definitization.

Provide the planned contract incentives:

Provide the specific incentive structure.  Indicate how the incentive structure will motivate contractor behavior resulting in the cost, schedule, and performance outcomes required by the government for the contract and the program as a whole.

If more than one incentive is planned for a contract, the strategy should explain how the incentives complement each other and do not conflict with one another.

Management information requirements. Discuss, as appropriate, what management system will be used by the Government to monitor the contractor’s effort. If an Earned Value Management System (EVMS) is to be used, discuss the methodology the Government will employ to analyze and use the earned value data to assess and monitor contract performance. In addition, discuss how the offeror's/contractor's EVMS will be verified for compliance with the American National Standards Institute/Electronics Industries Alliance (ANSI/EIA) Standard-748, Earned Value Management Systems, and the timing and conduct of integrated baseline reviews (whether prior to or post award). (See 34.202.) (FAR 7.105(b)(11).

Summarize the financial reporting that will be required by the contractor on each contract, including requirements for Earned Value Management.

Identify the source selection evaluation approach (e.g., Trade-off or Lowest Price Technically Acceptable) and briefly summarize planned procedures (10 USC 2305).

Highlight the considerations influencing the proposed source selection procedures.  Indicate how these may change from phase to phase.

State the timing for submission and evaluation of proposals.  Identify the criteria that will be used to select the winning bidder.  Indicate how those criteria reflect the key government goals for the program.

Sources

List the known prospective sources of supplies or services that can meet the need. Consider required sources of supplies or services (see FAR Part 8), and sources identifiable through databases including the government-wide database of contracts and other procurement instruments intended for use by multiple agencies available at https://www.contractdirectory.gov/contractdirectory/.

Based on results of market research, identify the specific opportunities for:

  - small business,

  - veteran-owned small business,

  - service-disabled veteran-owned small business,

  - HUBZone small business,

  - small disadvantaged business, and

  - women-owned small business concerns, and

specify how small business participation has been maximized at both the direct award and subcontracting levels (see FAR Part 19).

Contract Bundling or Consolidation

If the contract is a bundled acquisition (consolidating two or more requirements for supplies or services, previously performed under smaller contracts, into a single contract that is likely to be unsuitable for award to a small business), indicate the specific benefits anticipated to be derived from bundling. Reference FAR section 7.107, Acquisition Planning. (15 USC 644)

If applicable, identify the incumbent contractors and the contracts affected by the bundling.

Per DFARS section 207.170, if the acquisition strategy proposes consolidation of contract requirements with an estimated total value exceeding $6 million, provide: (1) the results of market research; (2) identification of any alternative contracting approaches that would involve a lesser degree of consolidation; and (3) a determination by the senior procurement executive that the consolidation is necessary and justified.

Subcontracting Plan / Small Business Participation.  When FAR Subpart 19.7 applies, the acquisition strategy should establish maximum practicable individual socio-economic subcontracting goals, meaningful small business work, and incentives for small business participation.

Outline planned award evaluation criteria concerning small business utilization in accordance with FAR Subpart 15.3, and DFARS Subpart 215.3 regarding source selection; and

Summarize the rationale for the selection of the planned subcontract tier or tiers.

Indicate how prime contractors will be required to give full and fair consideration to qualified sources other than the prime contractor for the development or construction of major subsystems and components.

Identify any special contracting considerations: list any unique clauses or special provisions (e.g., any contingent liabilities (i.e., economic price adjustment or business base clauses, termination liability, etc.)) or special contracting methods (see FAR Part 17) included in the contract; list any special solicitation provisions or FAR deviations required (see FAR Subpart 1.4).

Identify any planned use of government-furnished special test equipment, unique tooling, or other similar contractual requirements.

Discuss any associated considerations, such as its availability or the schedule for its acquisition (FAR 7.105(b)(15)).

Discuss any Government information, such as manuals, drawings, and test data, to be provided to prospective offerors and contractors. Indicate which information that requires additional controls to monitor access and distribution (e.g., technical specifications, maps, building designs, schedules, etc.), as determined by the agency, is to be posted via the enhanced controls of the GPE at http://www.fedbizopps.gov (see 5.102(a)). (FAR 7.05(b)16))

Specify how testing and systems engineering requirements, including life-cycle management and sustainability requirements, have been incorporated into contract requirements.  Ensure contract requirements support test strategies (e.g. DT&E, OT&E, etc.).

Identify the engineering activities to be stated in the RFP and required of the contractor to demonstrate the achievement of the reliability and maintainability design requirements.

Provide a table (see example Table 4) to specify how the sustainment key performance parameter thresholds have been translated into reliability and maintainability design and contract specifications. Table 4, as presented here, is a sample.  The actual format of this table may be varied to suit the nature of the procurement or to add additional requirements.   The reliability threshold is often expressed as Mean Time Between Failure (MTBF). Use the appropriate life units (e.g., hours, cycles, etc.).  “MTTR” is “mean time to repair;” “N/A” may be entered if an item is not applicable.

| Reliability and Maintainability Requirements |  |  |
| --- | --- | --- |
| Parameter | Threshold | Contract Specification Requirement |
| Reliability (e.g., MTBF) |  |  |
| Maintainability (e.g., MTTR) |  |  |

Table 4. Reliability and Maintainability Requirements

To the extent applicable, describe the test program of the contractor and the Government. Describe the test program for each major phase of a major system acquisition. If concurrency is planned, discuss the extent of testing to be accomplished before production release (FAR 7.105 (b)(13)).  Ensure this aligns with the test strategy.

Indicate whether a warranty is planned, and if so, specify the type and duration; summarize the results of the supporting Cost Benefit Analysis. (See FAR Subpart 46.7 and DFARS Subpart 246.7.)

If this strategy is for Milestone C or later, indicate whether the production program is suited to the use of multiyear contracting (10 USC 2306b).  Indicate any plans for multiyear contracting and address compliance with 10 USC 2306c and Office of Management and Budget (OMB) Circular A-11.

Indicate whether leasing was considered (applies to use of leasing in the acquisition of commercial vehicles and equipment) and, if part of the strategy, economically justify that leasing of such vehicles is practicable and efficient and identify the planned length of the lease.

Modular Contracting (Major IT Programs only).  Quantify the extent to which the program is implementing modular contracting (41 USC 434).

Payment.  Identify financing method(s) planned and whether these provision(s) will be flowed down to subcontractors.  Indicate if early progress payments will be traded off for lower prices in negotiations.

Address contractor versus government performance. Address the consideration given to OMB Circular No. A-76 (see Subpart 7.3).  Address inherently governmental functions and the consideration given to Subpart 7.5 (FAR 7.105(b)(9) and (FAR 7.105(b)(10)).

Discuss the expected consequences of trade-offs among the various cost, capability or performance, and schedule goals (FAR 7.105(a)(6)).

Unless presented elsewhere in this document, provide acquisition considerations (FAR 7.105(b)(5)) to include:

For each contract contemplated, discuss use of multiyear contracting, options, or other special contracting methods (see Part 17); any special clauses, special solicitation provisions, or FAR deviations required (see Subpart 1.4); whether sealed bidding or negotiation will be used and why; whether equipment will be acquired by lease or purchase (see Subpart 7.4) and why; and any other contracting considerations. Provide rationale if a performance-based acquisition will not be used or if a performance-based acquisition for services is contemplated on other than a firm-fixed-price basis (see 37.102(a), 16.103(d), and 16.505(a)(3))

For each order contemplated, discuss:

For information technology acquisitions, how the capital planning and investment control requirements of 40 U.S.C. 11312 and OMB Circular A-130 will be met (see 7.103(v) and Part 39); and

Why this action benefits the Government, such as when (1) The agency can accomplish its mission more efficiently and effectively (e.g., take advantage of the servicing agency’s specialized expertise; or gain access to contractors with needed expertise); or (2) Ordering through an indefinite delivery contract facilitates access to small disadvantaged business concerns, 8(a) contractors, women-owned small business concerns, HUBZone small business concerns, veteran-owned small business concerns, or service-disabled veteran-owned small business concerns.

For information technology acquisitions using Internet Protocol, discuss whether the requirements documents include the Internet Protocol compliance requirements specified in 11.002(g) or a waiver of these requirements has been granted by the agency’s Chief Information Officer.

For each contract (and order) contemplated, discuss the strategy to transition to firm-fixed-price contracts to the maximum extent practicable. During the requirements development stage, consider structuring the contract requirements, e.g., contract line items (CLINS), in a manner that will permit some, if not all, of the requirements to be awarded on a firm-fixed-price basis, either in the current contract, future option years, or follow-on contracts. This will facilitate an easier transition to a firm-fixed-price contract because a cost history will be developed for a recurring definitive requirement.

Provide any other pertinent information that may enhance understanding of the contracting strategy.

Discuss other considerations, as applicable: (1) Standardization concepts, (2) The Defense Production Act, (3) The Occupational Safety and Health Act, (4) Support Anti-terrorism by Fostering Effective Technologies Act of 2002 (SAFETY Act) (see Subpart 50.2), (5) Special requirements for contracts to be performed in a designated operational area or supporting a diplomatic or consular mission, and (5) Any other matters germane to the plan not covered elsewhere. (FAR 7.105(b)(20)(i)(iii-v)(vii-viii)).

Technical Data Rights Strategy (formerly the Data Management Strategy). Summarize the Technical Data Rights strategy for meeting product life-cycle data rights requirements and to support the overall competition strategy.  Include:

Analysis of the data required to design, manufacture, and sustain the system as well as to support re-competition for production, sustainment, or upgrade. The strategy should consider, but is not limited to, baseline documentation data, analysis data, cost data, test data, results of reviews, engineering data, drawings, models, and Bills of Materials (BOM).

Identify what deliverables (Contract Data Requirements List (CDRL)) it must acquire based upon the unique nature of the supplies or services being acquired and how those supplies or services will be used by, e.g., the warfighter.

Identify the estimated cost of those CDRL

Describe how the program office would store, manage and review the content of those CDRLs, and identify who will be responsible for ensuring those activities are performed.

How the program will provide for rights, access, or delivery of technical data the government requires for the system's total life cycle sustainment. Include analysis of data needs to implement the product support life cycle strategy including such areas as materiel management, training, Information Assurance protection, cataloging, open architecture, configuration management, engineering, technology refreshment, maintenance/repair within the technical order (TO) limits and specifically engineered outside of TO limits, and reliability management.

Identify what IP rights the Government will acquire to which CDRLs and the rationale for acquiring those levels of license rights.

Explain how the acquisition of those rights is consistent with 10 USC 2320, DFARS 227.71/227.72, and the life-cycle needs of the program.

Identify the DFARS clauses that will be included into the resulting contracts

Identify the estimated cost of the IP rights to those CDRLs.

Describe the process the program will follow to question or challenge contactor assertions or markings.

Describe the approach for maintaining the software and its related documentation once software maintenance is transferred from the OEM

Describe the use of withholding or incentives specific to performance in the area of data management

Describe to what extent an Integrated Data Environment (IDE) will be used during contract performance, including any required interfaces to government data systems/repositories, how those requirements will be satisfied, the digital format standards to be used, and why the team selected those standards.

Describe what evaluation criteria will be used to evaluate IP rights proposed by offerors during source selection

The business case analysis calculation, conducted in concert with the engineering tradeoff analysis, that outlines the approach for using open systems architectures and acquiring technical data rights.

Analyze the contractor's economic interest in such IP that potential offerors developed exclusively at private expense by performing market research.

Analyze the Government's costs to acquire, maintain, store, retrieve and protect the data, repair/maintenance/overhaul philosophies, spare/repair parts considerations, and whether procurement of the items, components or processes can be accomplished on a form, fit or function basis

Compare the results of each analysis to each other to justify an investment decision to implement (or not implement) an OSA or acquire (or not acquire) rights in technical data and SW for the program

The cost-benefit analysis of including a priced contract option for the future delivery of technical data and intellectual property rights not acquired upon initial contract award

Based upon its TRA the program office determines whether critical technology elements will mature to such an extent that a component that cannot be repaired at the present can be repaired by a depot-level maintenance facility in the future.

The requirements community can be convinced over time that a company other than the software developer can deliver software patches/updates of equivalent quality at a cheaper price.

The program office will acquire Unlimited/Unrestricted Rights to all deliverables needed for the life-cycle of the weapon system as part of the basic contract.

Analysis of the risk that the contractor may assert limitations on the government's use and release of data, including Independent Research and Development (IRAD)-funded data (e.g., require the contractor to declare IR&D up front and establish a review process for proprietary data).

Review all relevant contracts, including CDRL content

Review copies of FAR/DFARS standard clauses incorporated by reference into those contracts

Review any asserted rights restrictions made by the contractor prior to award of those contracts

Review copies of the deliverables submitted under those contracts to which are affixed restrictive markings that indicate what license rights the Government acquired to those deliverables

Review copies of the contractor's accounting records that identify the sources of funding used to create the items, components or processes associated with those deliverables

Review Contract Performance Reports that may identify those sources of funding.

Contract Management

Contract administration. Summarize how the contract(s) will be administered. Include how inspection and acceptance corresponding to the work statement’s performance criteria will be enforced (see FAR Part 42).

Priorities, allocations, and allotments. When urgency of the requirement dictates a particularly short delivery or performance schedule, certain priorities may apply. If so, specify the method for obtaining and using priorities, allocations, and allotments, and the reasons for them (see FAR Subpart 11.6).

Environmental and energy conservation objectives.  Discuss all applicable environmental and energy conservation objectives associated with the acquisition (see Part 23), the applicability of an environmental assessment or environmental impact statement (see 40 CFR 1502), the proposed resolution of environmental issues, and any environmentally-related requirements to be included in solicitations and contracts (see 11.002 and 11.303) (FAR 7.105(b)(17)).

Security considerations. For acquisitions dealing with classified matters, discuss how adequate security will be established, maintained, and monitored (see Subpart 4.4).For Information Technology acquisitions, discuss how agency information security requirements will be met. For acquisitions requiring routine contractor physical access to a Federally-controlled facility and/or access to a Federally-controlled information system, discuss how agency requirements for personal identity verification of contractors will be met (see Subpart 4.13) (FAR 7.105(b)(18)).

Cost and Funding

Investment Program Funding and Quantities.  Provide a copy of the program’s “Investment Program Funding and Quantities” Chart, with a current “as of date” (see the sample in Figure 4).  The current template and instructions for the development of this chart are provided at: https://atwmwadn01n.ext.rsrc.osd.mil/DABSchedule/Questions.aspx?text=IPT (login with password or Common Access Card required).

Figure 4. Example “Investment Program Funding and Quantities” Chart

If the chart reflects funding shortfalls, indicate how they will be addressed and state the programmatic impact if they are not.

If the program is jointly funded, provide a separate chart reflecting the funding contributions required of each joint participant.

Provide and briefly explain funding support from the Working Capital Fund.

If multiple program increments are in progress, funding will be tracked separately for each increment (e.g., for subsets of the program that will be subject to a separate Acquisition Program Baseline).  Provide separate charts for each increment.

Cost. Indicate the established cost goals for the increment and the rationale supporting them.

If a Technology Development Strategy, indicate the Affordability Target that has been established for the program (initially, average unit acquisition cost and average operational support cost per unit). The affordability target should be presented in the context of the resources that are projected to be available in the portfolio(s) or mission area(s) associated with the program under consideration. For new start programs, provide the quantitative analytical basis for determining that the resources expected to be available in the portfolio/mission area can support the program under consideration.  Employ a graphic to illustrate.

Acquisition strategies for ACAT I programs will specify (no more than one page) how the procurement rate and schedule were set, with reference to Economic Order Quantity (EOQ) and the affordability target set at Milestone A, as adjusted at Milestone B.

“Should Cost”

Summarize the application of should-cost analysis to the acquisition.  Identify the should-cost initiatives that have been planned for the program.  Specify how the associated “should cost targets” will be used as a basis for contract negotiations and contract incentives, and to track contractor, PEO, and PM performance.

Provide a table identifying the program “Should Cost” initiatives and associated targets.

For more information, please see the ACE Should-Cost folder.

Explain how the cost management approach adequately considers funds management. Identify any contingent liabilities (award fee, special incentives, economic price adjustment, business base clauses, termination liability, etc.) planned for or associated with the program. Identify which contingent liabilities have been funded.  Summarize the plan to obtain approval for any unfunded contingencies (see DFARS 217.171.a.(4) and 217.172.(e)).

For acquisitions of Federal Information Processing resources with expected costs greater than $100 million, identify the key outcome performance measures. Indicate the tracking system that will be used to measure and report on selected outcome performance measures.

Summarize plans to control program costs, specifically Program Acquisition Unit Cost, Average Procurement Unit Cost, and Life-Cycle Cost. List and describe cost control tools and processes.

Summarize the process to update estimates (e.g., x months before each decision review or x months before beginning each increment).

Describe the design-to-cost objective(s) and underlying assumptions, including the rationale for quantity, learning-curve, and economic adjustment factors. Describe how objectives are to be applied, tracked, and enforced. Indicate specific related solicitation and contractual requirements to be imposed (FAR 7.105 (a)(3)(ii)).

Resource Management. Address program resource requirements; consider changes in effort as the program progresses.

Program Office Staffing and Organization

Manning Profile. Provide a time-phased workload assessment identifying the manpower and functional competencies required for successful program execution. Considering the overall, technical, acquisition, sustainment, and management approach, specify the number of personnel, by functional area, that are required to manage this program for the next phase and through fielding.   Include a projected manning profile based upon the overall approach and program schedule for government, Systems Engineering and Technical Assistance, and Federally Funded Research and Development Center(s) support.

Organization Chart. Provide an organization chart reflecting program manning requirements by functional area.  Identify the Services filling billets for a joint program.  Prepare a table to indicate whether billets are military, civilian, or contractor, the seniority level of the billets, and whether the billets are currently filled or vacant.  (See Table 5.)

| PROGRAM MANNING REQUIREMENTS |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Billet ID | Billet Name | (If Joint) DoD Component | Manning Type | Seniority Level | DAWIA Level | Fill Status |

Table 5.  Notional table of Program Manning Requirements

Acquisition Chain of Authority. Indicate specific lines of programmatic authority. Show how the authority chain meets the requirements identified in DoD Directive 5000.01, paragraph E.1.1.26.

Identify the primary stakeholders. Indicate the planned organization to effectively manage the program and ensure all stakeholders are involved (Integrated Product Teams (IPT), boards, reviews, etc.). If applicable, indicate how the contractor will be involved in program IPTs. Summarize the anticipated business management relationship between (1) the program office and the contractor, and (2) the program office and other government agencies.

Requirements Community Involvement.  Specify how the customer-representing organization will interface with the program management office and acquisition chain of command to provide for timely and effective review of requirements and/or cost trade-offs.  Define levels of authority required to change requirements of various types.

International Involvement

Indicate any limitations on foreign contractors being allowed to participate at the prime contractor level.

International Cooperation.

Summarize any plans for cooperative development with foreign governments or cognizant organizations.  List the MOAs in place and identify the contracting activities.

Summarize plans to increase the opportunity for coalition interoperability as part of the developing DoD program.

Employ the AT&L-developed template to provide a coalition interoperability section in the Acquisition Strategy.  Using the template will satisfy the cooperative opportunities document requirement of 10 USC 2350a.

Foreign Military Sales.  Specify the potential or plans for Foreign Military and/or Direct Commercial Sale and the impact upon program cost due to program protection and exportability features.

Industrial Capability and Manufacturing Readiness.

Industrial Capability. Summarize the results of industrial base capability analysis (public and private) to design, develop, produce, support, and, if appropriate, restart the acquisition program. Specify the impact of this acquisition approach on the national technology or industrial base and the analysis used to make this determination. If there is an impact, summarize the industrial base constraints, how they will be managed, and the plan for future assessment, including frequency.

Industrial and Manufacturing Readiness (not applicable to software-intensive programs without production components). Estimate the risk of industry being unable to provide program design or manufacturing capabilities at planned cost and schedule. Identify the Manufacturing and Quality Management systems and summarize how they will contribute to minimizing cost, schedule, and performance risks throughout the product life cycle.

Sustaining Industrial Capabilities. Summarize the make-or-buy approach to establish and maintain access to competitive suppliers for critical areas at system, subsystem, and component level (e.g., requiring an open-systems-architecture or a make-or-buy plan).  List critical items and their sources.  When the analysis indicates that the needed industrial capabilities are in danger of being lost, the strategy should indicate whether government action is required to preserve the industrial capability. The strategy should also address product technology obsolescence, replacement of limited-life items, regeneration options for unique manufacturing processes, and conversion to performance specifications at the subsystems, component, and spares levels.

Identify any planned or completed MOAs.

Life-Cycle Signature Support

If a Technology Development Strategy, provide a table (see example Table 6) that indicates the program life-cycle signature support requirements.  Identify the mission data type (signatures, electronic warfare integrated reprogramming, order of battle, geospatial intelligence, and system characteristics and performance data sets); specific subcategories, if known (Radar, Thermal, Acoustic, etc.); the domain (Space, Air, Land, Naval, Missile Defense, etc.); subcategories within the domain (e.g., for Air domain: ‘Fighter Aircraft’); and data fidelity required, if known (e.g., dB, °C, resolution, Hz, etc.). If additional or more-specific requirements have been identified, they should be included.

| Life-Cycle Signature Support Requirements |  |  |  |  |
| --- | --- | --- | --- | --- |
| Mission Type | Mission Type Subcategory | Domain | Domain Subcategory | Data Fidelity |

Table 6.  Notional Table of Life-Cycle Signature Support Requirements

Life-cycle signature support funding requirements will be reflected in the program funding summary (see Paragraph 8 and Figure 4).

Military Equipment Valuation.  Federal accounting standards require military equipment to be capitalized on the Department’s financial statements.  For Milestone C and the Full-Rate Production Decision, provide the following information for any program, project, product, or system that has deliverable end items with a unit cost at or above $100,000 (the current capitalization threshold):

A level 2 work breakdown structure (as described in MIL_HDBK-881A) for reporting  Military Equipment Valuation and Accountability;

The end item(s) meeting the unit cost threshold (i.e., $100,000);

The government furnished property that will be included in the end item;

Other deliverables that will accompany the end item (e.g., manuals, tech data, etc.); and

Other types of deliverables that will be purchased with program funding (e.g., initial spares, support equipment, special tooling and test equipment, etc.), but cannot be directly attributed to a specific end item.

(NOTE: The unit cost can be calculated by summing the estimated cost of the end item with the estimated costs of all associated government furnished equipment, training manuals, technical data, engineering support, etc., NOT including spares and support equipment.  For additional information, see:

- http://www.acq.osd.mil/pepolicy/training_tools/quick_reference_tools.html; or

- http://www.acq.osd.mil/pepolicy/training_tools/bfma_instructions.html.)

Test Strategy

Provide a brief summary of your test strategy.  Summarize the testing milestones and focus of each phase, estimated timing, potential risks, and planned resources & funding to support it.

Summarize how the testing strategy will be captured & supported in the RFP.

Identification of participants in acquisition plan preparation. List the individuals who participated in preparing the acquisition plan, giving contact information for each (FAR 7.105(b)(22)).

URL: https://acc.dau.mil/GetAttachment.aspx?id=288191&pname=file&aid=44021&lang=en-US